Lessons Learned (2nd iteration)

1:1 Learning Initiative Pilot

If your school or school system is contemplating a 1:1 learning environment, you may wish to heed the following Lessons Learned from the 1:1 Learning Initiative Pilot:

First and foremost:  Take Time to Plan!

- Six months to a year is a reasonable planning timeline.

- Make sure that sustainability is part of the overall plan at the beginning of the project.

- Think infrastructure first!  Do not deploy computers until the building has reliable high speed Internet access throughout the campus.

- Infrastructure also includes the school’s electrical grid and other facility changes that will involve your maintenance staff.  Get them involved in the conversations early.

- Make sure technology personnel (building-level technology facilitator and technician) are hired and in place before any computers are ordered.

- Create a climate of buy-in at all levels of the project: central office, building-level teachers and administrators, parents and students, and the community.  Involve all stakeholders in the planning process.

  - Visit other schools that have experience in the 1:1 learning environment you have chosen.  Allow everyone to see what teaching and learning looks like in these environments and give them a chance to talk with those already participating.

  - If finances allow, find a state or national conference that has sessions featuring 1:1 teachers, administrators, and students.  Insist that everyone visit the exhibits to become aware of all the options that can support their teaching in this new environment.

- Simultaneously, temper expectations.

  - While student attendance and discipline incidents should decrease early in the project, the effects will probably level off over time.

  - Improved student achievement may gradually improve—or it may wait until state testing formats and content are revised to reflect the way students are learning in the 1:1 environment.

  - Learning to teach in a 1:1 environment takes time, energy, and commitment.  Initially, not every teacher will be thrilled with this new way of doing business.

- Plan to give every faculty member and administrator the same technology.  Modeling and consistency are important, and everyone needs the same device whether it is a laptop, PDA, cell phone, etc.

  - Make sure administrators model the use of the adopted technology!  Teachers want to see their principals use a laptop, not the old desktops in their offices.

- Focus on teacher professional development and empowerment.

  - Give teachers their laptops first, preferably in the spring before whole-school roll-out at the beginning of the upcoming school year.

  - Provide professional development opportunities throughout the summer before whole-school roll-out.

  - Rely upon the school’s Media and Technology Advisory Committee (MTAC) and/or the school’s Leadership Team to help make logistical and professional development decisions.  This improves teacher buy-in.

Consider these specific recommendations:

Leadership

- This must be considered an LEA initiative and an instructional initiative, not just a technology initiative.  Thus, all central office staff must embrace the vision, create opportunities to talk about its importance, and plan events and PD around it.

- A high-level Leadership Team should be formed immediately once the initiative is adopted and should meet both face-to-face and/or virtually at least bi-weekly during the first year of the project.

  - The initiative’s Leadership Team should be comprised of the Associate Superintendent, Technology Director, Director of C&I, Director of Finance, the principals of the schools affected, and at least one technology facilitator and one media coordinator.

  - An Advisory Committee made up of the Superintendent, Board member(s), community member(s), parent(s), and student(s), supported by the Technology Director, that meets quarterly is an excellent PR opportunity.

- C&I and Finance must be involved in all high-level planning for this initiative.

- While the technology department will be ultimately responsible for the implementation of the project, the Leadership Team must reach consensus on all major decisions.

Infrastructure

- You will need more access points than you initially plan.  Consider at least a wireless boost in every classroom.

- Make sure you have wireless access in classroom trailers, the gym and cafeteria, and even the school parking lot if possible.  Students and teachers will use the 1:1 devices constantly, everywhere.  Be prepared!

- CIPA, E-Rate, and the federal government will be watching; viruses are opportunistic.  Route all Internet traffic through your servers, even when the devices are off-campus.

  - Provide a secure server to house and back-up student work rather than relying on individual student flash drives.

- Consider core classroom equipment (interactive whiteboard, projector, scanner, digital camera, flip video camera, classroom response systems, digital science equipment, interactive wireless pad) as a primary part of your initial infrastructure.  Installing this equipment as teachers are given their laptops gives them opportunity to learn how to use the tools effectively before adding student computers into the equation.

  - Data projectors mounted from the ceiling, rather than being deployed on carts, untether teachers from the front of the classroom.  The fewer barriers to a teacher’s moving about the classroom will result in better use of resources and more student time on task.

  - Interactive white board hardware is changing rapidly, becoming more manageable and less expensive.  Investigate carefully before buying.

- Include electrical upgrades as part of the infrastructure investment.  Ensure that all classrooms have adequate plugs for individual charging of batteries—or invest in a charging station/cart for each classroom.

Laptops

- Adoption seems to come more rapidly with tablets, especially from the teaching community because a large portion of teaching community still prefers to hand-write instead of type. It has been an easier transition, especially for math and science teachers, because writing mathematic equations and scientific notation is much faster than typing.

  - The major concern with tablets is durability, especially of the styluses and screen latches.

- Include loaner computers, extra battery chargers, replacement batteries, electronic textbook fees, and laptop bags in your initial budget—and make them a part of your TCO sustainability figures.

  - Consider loaners that will equal 10% of the number of computers currently in the school.

- Laptop screens are fragile; consider mandating separate laptop and book bags if it is impossible to acquire electronic textbooks and resources in all courses.

Other 1:1 Options

- Smart phones, iPods, iPod Touches, tablets, netbooks, etc. are now viable options for 1:1 initiatives, and are often less expensive than laptops.

- The important question to consider as you make this choice is your ultimate educational goal:  What do we want our teachers and students to be able to do with these machines?  Is it consumption?  Is it creativity?  Is it cost?  Is it access?  The careful consideration of these answers will determine your choice.

  - The advent of cloud computing means that individual machine or building-level storage no longer has to be a major consideration when having the netbook discussion.

  - Occasionally schools or individual teachers can opt to involve students’ personal cell phones in classroom activities and/or assignments.  This should be discussed at a faculty meeting (or, at the very least, an MTAC meeting) and during a PTSO meeting before it becomes general practice.

Personnel

- Choose the principal who will implement the 1:1 environment carefully.  Individuals

  - who are familiar and comfortable with the change process,

  - who have a vision of what 1:1 learning in a school can do—and who can inspire teachers to embrace that vision,

  - who can model technology use, and

  - who are at ease with shared decision-making

tend to be the most successful administrators of a technology-rich school.

- Both a technology facilitator and technician should be hired to partner with the school library media coordinator to collaborate with teachers to create an effective, efficient teaching and learning environment.  The North Carolina Educational Technology Plan (2007) recommends the following ratio:

  - A minimum of one technology facilitator per school, with additional positions once a school surpasses 1000 students.

  - One Technology Assistant per school, per 1000 students.

  - Once Technician I, II, or III for every 400 computers.  At least one of the Technicians should be a Technician III.

- Make sure the school’s media coordinator is involved from the beginning of the project.  The expectation should always be that the technology facilitator and the media coordinator, with the assistance of the technicians and media center staff, will form an instructional team that works with teachers and students to support and enhance teaching and learning.

- Consider forming a student technology team as soon as possible so that teachers and fellow students, as well as the media and technology team, have assistance quickly (and techie students have an opportunity to channel their expertise and experimental nature in positive directions). Consider giving students service learning credits or hours for their service on the student technology team.

Professional Development

- Since this is an overall educational (i.e.curriculum) initiative, all LEA professional development opportunities for these schools should be based on the assumption that 1:1 is the way of doing business, thus designing all PD to include opportunities to use the equipment.

- Both general and content-specific professional development should be provided for all participating teachers and administrators.

  - Occasional general PD for all teachers should be required so that everyone can embrace and absorb a shared vision, understanding, and approach to learning.

  - Most PD should be differentiated, based on individuals’ abilities, needs, and content area.

  - Ideally, collaborative project opportunities will arise during general, grade-level, and/or content-area PD that can be facilitated by the media and technology personnel team.

- Make sure that PD is provided on all new hardware, whether it’s computers, interactive white boards, digital cameras, etc.  All these resources will go unused unless teachers are given the opportunity to see their potential and learn how to use them effectively.

- The technology facilitator and the media coordinator can provide the ideal 1:1, just-in-time PD environment so necessary for this project’s success.

- Technology and media personnel should regularly survey staff for PD needs/requests and plan PD opportunities around the survey results.

- Technology and media personnel should also ask staff to evaluate all PD sessions and use those evaluations to meet the needs of participants during future training.

- Learning to teach in a 1:1 environment takes time.  Provide as many opportunities for teachers to carve out larger blocks of time for lesson planning and collaboration as possible.  This time does not include teachers’ daily planning periods.

- Assessment in a 1:1 learning environment is very different than in a traditional environment.  Common rubrics, crafted by teachers together over time, help everyone move into this new strategy for evaluating student work.

- Copyright is difficult for teachers to conceptualize, understand, and teach their students.  Find various, differentiated, and frequent opportunities for teachers to learn and articulate these concepts.

- Use the 1:1 technology to provide training and support for teachers, making sure that they have opportunities to learn from and enjoy each other virtually as well as face-to-face.

- Include parents, students, and even the community in your professional development plan.

  - Parents need initial information sessions so that they can join the school in supporting the educational focus of this 1:1 learning initiative.

  - As the project moves forward, the same parents (and community members) may benefit from learning how to use the technology for job skills and personal productivity.

  - Students need formal training on the use of the computers for educational purposes and the academic and social expectations that accompany this privilege.

District and School Policies

- While many school and district policies will have to be clarified and/or augmented, computer policies should reflect general school policies (ex. Bullying and cyberbullying are both similar; both should have immediate, severe, and identical/consistent punishments—with the possible addition of losing computer privileges for an appropriate length of time for dangerous behavior).

  - As 1:1 hardware becomes the norm in your school, consider the message behind loss of computer privileges.  Would you take away the use of a student’s pencil or textbook regardless of the offense?  Can you narrow a student’s access without jeopardizing his academic work?

  - Although the 1:1 pilot schools have not reported an increase in instances of bullying, an unfortunate reality is that teens are impetuous and immature.  Inappropriate cyber events will take place regardless of the amount of monitoring, hand-holding, and education you have provided—or how long your school has had a 1:1 environment.  Be ready immediately to intervene if a student’s mental or physical health is in danger.  Always be aware of undercurrents, both digital and face-to-face in your school.

- Ensure every teacher and administrator enforces the laptop policy consistently.

- One of the greatest challenges is the dual responsibility of keeping students safe and enabling the use of educationally appropriate, digital resources.  Consider the following:

  - If possible, allow teachers the privilege of unblocking appropriate websites immediately from their desks so that instruction, especially the teachable moment, is not interrupted.

  - Insist that teachers learn how to monitor student use of computers.

  - Also encourage teachers to determine when it is appropriate to request that students close their laptops or keep them in their bags--and empower them to do so.

  - Make sure that district and school technology personnel understand and appreciate the educational uses of online resources and services as well as their technical characteristics.

- Have an understanding with educators, school board members, and the community that your district and school AUPs are perpetual works-in-progress.  Revisit, and amend if necessary, at least once yearly.

- Make sure that everyone—students, teachers, administration, and parents—sign appropriate AUP documents after being provided appropriate training as to meaning and necessity.

- Provide district-managed insurance policies for all computers, but consider asking students/parents to contribute a nominal amount toward the cost of that policy.  Provide an easy-payment opportunity or even special service-learning projects for families that cannot afford the fee.

District and School Procedures

- Begin early to plan for laptop imaging, maintenance, storage, and distribution.  Re-visit these plans at least yearly.

- Take initial deployment and subsequent distribution seriously!  While it is important to commit that every student will have a computer, it is equally important to be able to track them.  All school-based personnel must be familiar with and adhere to district deployment and distribution procedures.

  - Design an initial distribution procedure that can be accomplished in an organized, “batched” process.  This can be by homeroom, by parent meeting, by grade level, or by subject area.

    - Make sure you have adequate staffing to ensure that distribution is orderly, paperwork is complete and filed, and machines are tracked.

    - At the end of the designated time/day, inventory all computers, check paperwork for any omissions, etc., and store or remove according to agreed-upon plan.

  - After initial distribution, yearly distribution can be made during freshman orientation and when upperclassmen pick up their schedules.  Again, make sure procedures are mapped out carefully, adequate staffing is available, and all workers understand and follow the plan.

- Make separate plans for distribution of machines not initially deployed and for new students entering the school.  Include in this plan procedures for the collection of equipment from students leaving the school or the LEA.

  - If all high schools in the system are 1:1, consider adopting a process that will allow the student to get his computer back at his new school.

- Design “loaner” procedures that allow students access to equipment without making it so attractive that they don’t feel the need to pay fees/adhere to school/district policy.

- Consider the 1:1 project an entirely new way of doing business.  Think about such issues as:

  - How the school system’s support for education can move to 24/7 since students and teachers will work 24/7.

  - How to provide a 21st Century, Web 2.0 teaching and learning environment within the constraints of student safety and the district’s technology and personnel capacity.

  - Which student documents will be saved to the school and/or district server(s).

  - Whether or not to provide portfolio software for all student work or just each student’s Graduation Project.

  - How to facilitate teacher and even student downloading of software and/or documents at point of need.

  - How to deal with parents who opt out of their child’s 1:1 opportunity either at school and/or at home so that the student still has the possibility of a successful academic experience.

  - Similarly, how to deal with parents who want to load printer drivers, etc. on their child’s computer to facilitate their own ease and efficiency.

  - How to calculate the Total Cost of Ownership for the 1:1 initiative so that the entire project can move forward, be maintained and upgraded, and sustained for future benefit of all students and teachers.

  - How to “grow your own” technology facilitators and help talented individuals pay for that certification.

Resources

- Provide resources such as secure servers for teachers and students to blog and post videos.  Consider protected digital resources such as TeacherTube, fizz, the NC LOR Project, and VoiceThread so that students may work within a protected Web 2.0 educational environment.

- Learning management systems such as Moodle and Blackboard provide platforms and an organization system for teachers.  If using Moodle, designate a server to house the platform.

  - Additionally, Microsoft OneNote offers a way for students to organize themselves in a virtual environment.  Get them started early, before they develop less effective organizational strategies.

- Choose a classroom monitoring system carefully, making sure it is compatible with your network configuration, equipment, and ways of doing business.  You may even consider whether the expense and distraction of a monitoring system outweighs the reassurance of surveillance.

- Set aside a graduated budget for resources.  Teachers need time to become familiar with their machines before they can understand what additional tools might be useful.  Likewise, technology changes rapidly.  Allocate amounts over time rather than in a single budget largess.

- Provide e-mail accounts for all students as a part of doing business in a 1:1 environment.

Public-Private Partnerships

- Schools and school systems cannot and should not do a 1:1 learning initiative in isolation.  Everyone in North Carolina can learn from each other and will benefit from this forward-thinking project.

- While private partnerships can help fund hardware and software, only the state can provide the technology personnel necessary for the success of this project.

- State funded resources such as NCVPS, Learn and Earn Online, NC WiseOwl, and other resources that will be provided as part of the Connectivity Project are invaluable to both teachers and students.  Every state-funded resource is an investment in equity and quality information for all students and teachers in the state.

- Conversations must begin immediately about how to sustain the 1:1 learning initiative over the coming years.  This should include refresh plans, ramped up personnel for schools, districts, and regions, and continued commitment to connectivity and state-funded resources.

- North Carolina’s schools/colleges of education that have Instructional Technology certification programs (077) should market their programs more widely to address the shortage of certified technology facilitators.